## Slide 1: PNNL-Thammasat Project Meeting
PNNL
Notes: Stock Image

## Slide 2: Agenda
Subcontract
Upcoming deliverables
Population & GDP data discussion
Additional GCAM questions
  Energy consumption
  EEP2018 sector names
Stakeholder Engagement (MEA, BMA, EPPO, EGAT)
Next steps

## Slide 3: Subcontract
Project Time Period: 02 May 2022 to 30 June 2023
Deliverables | Timeline | Milestones
Memo 1: 1 Page memo with list of official Thammasat team members and roles | May 2022 | Milestone 1
Workshop 1 Plan: 1 Page Agenda and Participant list for Workshop 1 | Jul 2022 | 
Memo 2: 2-3 Page Memo with Feedback on Input Data, Scenario 1 and Scenario 2 | Aug 2022 | Milestone 2
Workshop 2 Plan: 1 Page Agenda and Participant list for Workshop 2 | Nov 2022 | 
Memo 3: 2-3 Page Memo with Feedback on Scenarios 3, 4, 5 | Feb 2023 | Milestone 3
Workshop 3 Plan: 1 Page Agenda and Participant list for Workshop 3 | Apr 2023 | Milestone 4
GCAM Training Session | Timeline
GCAM training | Jun 2022
GCAM training | Sep 2022
GCAM training | Dec 2022
Workshops | Timeline
Workshop 1 with local institutions | Sep 2022
Workshop 2 with local institutions | Jan 2023
Workshop 3: ASEAN Best Practices workshop | Jun 2023
Objective: Explore policy and technology pathways to carbon neutrality (2050) and net-zero emission (2065) in Bangkok through technical analysis and engagement with local stakeholders and experts.

## Slide 4: Upcoming Deliverables
Memo 1 (Official list of team and roles)
  Person of Contact?
Workshop 1
  Content (introductory)
  Possible dates & times
  Who to invite
Planning sheet

## Slide 5: Population & GDP data
Variable | Assumptions | Data Sources
Population | Pre-2010 and post-2019 population growth rates consistent between regions | All regions 2010-2019: NSO Pre-2010 & post-2020 growth rates: UN
GDP | Pre-2011 and post-2020 GDP growth rates consistent between regions | All regions 2011-2020: NSO Pre-2011 growth rates: WB 2021-2037 growth rates: PDP2018
 | Post-2037 GDP growth rate constant everywhere | 
Raw Data: https://github.com/JGCRI/seasia/tree/main/data/Thailand/socioeconomic_inputs

## Slide 6: Energy consumption
With industrial feedstocks (Ref)
Without industrial feedstocks (Ref)
All Raw Data: https://github.com/JGCRI/seasia/tree/main/data/Thailand/scenario_outputs/initial_diagnostics
Local Data Sources: EPPO (by fuel) and EEP2018 (by sector)

## Slide 7: EEP2018 Energy Consumption Sectors
Industry
Buildings (commercial)?
Buildings (residential)
Industry (agriculture)
Transport
GCAM sectors
EEP2018
Energy Efficiency Plan 2018-2037 (EEP 2018): https://www.dede.go.th/ewt_w3c/ewt_dl_link.php?filename=index&nid=54495

## Slide 8: Stakeholder Engagement
MEA
  Invite Khun Nattanont to next PNNL-Thammasat meeting to give update?
Follow up with:
  BMA:
    Aine responded to Khun Akkarapol and BMA by email about their request for further info (28 Mar 2022)
  EPPO:
    Khun Por sent email on 3 Mar 2022 saying that EPPO wanted to talk to Prof. Bundit.
  EGAT:
    Email received from EGAT (Siripan) on 24 Mar 2022 acknowledging receipt and that they will respond about collaboration

## Slide 9: Next Steps
PNNL
  Integrate feedback
  Continue developing Scenario 1
Thammasat
  Memo 1 (Official list of team and roles)
  Workshop 1
Planning sheet